## Submissions
Request # | Date | CRDM # | Bldg. # | Description | $ Requested | PM | Project Status

## Issued
Date | CRDM # | Project # | Bldg. # | Description | Budget | PM | Final Cost | Project Status | Def. Maint., Design Flaw, Energy | CB Catagories | Emerg. | Critical , Deferred, Adaptation,Planned, On-going
2010-05-25 | FY07-0001 | P779440 | 529 | Science Engineering classroom shades | 20167 | Doyle |  |  | Def Maint | Arch | X
2010-06-21 | FY07-0002 | P779444 | 551 | S&R 2 4th flr filter vents | 3306.65 | Madrigal |  |  | Def Maint | HVAC | X
2010-06-21 | FY07-0003 | P779445 | 551 | S&R 2 3rd flr filter vents | 5015.21 | Madrigal |  |  | Def Maint | HVAC | X
2010-06-21 | FY07-0004 | P779446 | 551 | S&R 2 2nd flr filter vents | 3711.62 | Madrigal |  |  | Def Maint | HVAC | X
2010-06-21 | FY07-0005 | P779447 | 551 | S&R 2 1st flr filter vents | 609.3 | Madrigal |  |  | Def Maint | HVAC | X
2010-06-21 | FY07-0006 | P779448 | 532 | Garrison Gym AHU coil replacement | 6601 | Madrigal |  |  | Def Maint | HVAC | X
2010-06-29 | FY07-0007 | P779450 | 586 | Cameron asbestos tiles clean up | 9067 | Oliver |  |  | Def Maint | Safety | X
2010-06-30 | FY07-0008 | P779451 | 516 | E. Cullen exterior window cleaning | 5580 | Davis |  |  | Def Maint | Other
2010-06-30 | FY07-0009 | P779452 | 553 | Welcome Center replace glass panels | 5400 | Davis |  |  | Def Maint | Safety
2010-07-01 | FY07-0010 | P779453 | 550/ 551 | SR1 and SR2 Generator Addition | 32717 | Gill |  |  | Def Maint | Elec | X
2010-07-07 | FY07-0011 | P779454 | 516 | E. Cullen rm 122 reconfiguration | 1555.02 | Martin |  |  | Def Maint | Elec
2010-07-08 | FY07-0012 | P779455 | 553 | Continuing Education AHU-2 | 15446 | Martin |  |  | Def Maint | HVAC | X
2010-07-08 | FY07-0013 | P779456 | 545 | SERC emergency 15 KV switch | 7774.54 | Bartow | 7774.54 | Closed | Def Maint | Elec | X
2010-07-08 | FY07-0014 | P779457 | 593 | HSC dock & corridor door replacement | 20582 | Brungardt |  |  | Def Maint | Arch | X
2010-07-08 | FY07-0015 | P779458 | 593 | HSC elevator hydraulic cylinder replacement | 46263 | Rahurkar |  |  | Def Maint | Elec | X
2010-07-09 | FY07-0016 | P779459 | 551 | S&R 2 lab 228 water damage & mold remediation | 8582.87 | Davis | 8582.87 | Closed | Def Maint | Safety | X
2010-07-09 | FY07-0017 | P779460 | 590 | Hilton Continuing Ed window replacement & re-seal | 6452 | Davis | 6452 | Closed | Def Maint | Arch | X
2010-07-09 | FY07-0018 | P779461 | 551 | S&R 2 restroom fixture replacement | 24953.44 | Jenkins |  |  | Def Maint | Plumbing | X
2011-03-03 | FY07-0019 | P779462 | 551 | S&R 2 hallway abatement & flooring | 96320.61 | Davis |  |  | Def Maint | Safety | X
2010-07-12 | FY07-0020 | P779463 | 581 | Engineering D3 roof assessment | 5000 | Oliver |  |  | Def Maint | Arch
2010-07-12 | FY07-0021 | P779464 | 586 | Cameron emergency mold remediation | 56961.83 | Oliver |  |  | Def Maint | Safety | X
2010-07-12 | FY07-0022 | P779465 | 516 | E. Cullen 502D drain line for roof catch pan | 975 | Oliver | 975 | Closed | Def Maint | Plumbing
2010-07-15 | FY07-0023 | P779466 | 516 | Flooding mechanical rm Cullen fountain | 7100 | Rahurkar |  |  | Def Maint | Plumbing | X
2010-07-21 | FY07-0024 | P779468 | 509 | MD Anderson water in basement, test & clean | 25082.5 | Jenkins |  |  | Def Maint | Safety | X
2010-07-21 | FY07-0025 | P779469 | 593 | HSCA new condensate drains AHU | 7513.7 | Madrigal |  |  | Def Maint | HVAC | X
2010-07-15 | FY07-0026 | P779467 | 585 | GSB water heater tank replacment | 7250 | Wright |  |  | Def Maint | Plumbing
2010-07-21 | FY07-0027 | P779470 | 551 | S&R 2 lab OAHU repairs | 15761.56 | Martin |  |  | Def Maint | HVAC
2010-07-27 | FY07-0028 | P779471 | 516 | E. Cullen 3rd floor lobby lighting | 3320 | Rahurkar |  |  | Def Maint | Arch | X
2010-07-30 | FY07-0029 | P779472 | 550 | S&R 1 emergency vacuume pump | 22182.08 | Madrigal |  |  | Def Maint | Elec
2010-08-04 | FY07-0030 | P779473 | 581 | Engineering D2 envelope assessment | 88485 | Oliver |  |  | Def Maint | Arch |  | Deferred
2010-08-04 | FY07-0031 | P779474 | 509 | MD Anderson exterior façade | 268201.58 | Oliver |  |  | Def Maint | Arch | X
2010-08-05 | FY07-0032 | P779475 | 519 | DPS roof & waterproof analysis | 14189.09 | Davis |  |  | Def Maint | Arch | X
2010-08-18 | FY07-0033 | P779476 | 509 | MD Anderson cooling system | 96250 | Jenkins |  |  | Def Maint | HVAC | X
2010-08-24 | FY07-0034 | P779477 | 499 | Emergency plumbing infrastructure repairs | 14022.53 | Gill |  |  | Def Maint | Plumbing | X
2010-08-24 | FY07-0035 | P779478 | 550 | S&R2 faulty gas valves replacement | 7488.52 | Wright |  |  | Def Maint | Safety | X
2010-08-25 | FY07-0036 | P779479 | 512 | Modular office park restroom awning | 3630 | Davis |  |  | Def Maint | Arch | X
2010-12-17 | FY07-0037 | P779506 | 551 | SDS vent stack smoke test | 2500 | Gill |  |  |  | Plumbing | X | Critical
2011-03-07 | FY07-0038 | P779507 | 545 | SERC exterior glass replacement | 14961 | Wiesman |  |  |  | Safety | X | Critical
2011-01-03 | FY07-0039 | P779508 | 579 | Engineering ADA biomedical lab S-143 | 8100 | Harless |  |  |  | L&M | X | Critical
2011-02-17 | FY07-0040 | P779512 | 547 | PGH rrom sign replacement 4th, 5th and 6th Floor | 6000 | Villareal |  |  |  | Other |  | Deferred
2011-02-24 | FY07-0041 | P779514 | 516 | VP Research Suite Asbestos training | 350 | Howard |  |  |  | L&M | x | Deferred
2011-02-28 | FY07-0042 | P779520 | 516 | Presidents Suite Glass Replacement | 6684.12 | Davis |  |  |  | Other |  | Deferred
2011-10-17 | FY07-0043 | P779616 | 523 & 594 | AGL Complex and EERC high voltage overhead and transformer repairs | 4189.66 | Rahurkar |  |  |  | Elec | x | Critical
2009-10-10 | FY08-0001 | P779344 | 586 | Cameron elevator renovation | 12248.51 | Theriot | 12248.51 | Closed | Def Maint | Elec | X
2009-12-16 | FY08-0002 | P779345 | 547 | PG Hoffman roof repairs | 4900 | Barnes | 4900 | Closed | Def Maint | Arch
2010-01-07 | FY08-0003 | P779347 | 543 | Architecture water seal rm 214 | 30591 | Oliver | 24069.91 | Closed | Def Maint | Arch | X
2010-01-07 | FY08-0004 | P779348 | 503 | Technology loading dock repairs | 17490 | Oliver | 17490 | Closed | Def Maint | Arch | X
2010-01-15 | FY08-0005 | P779350 | 543 | Architecture lighting & life safety | 111812.58 | Oliver |  |  | Def Maint | Safety
2010-01-13 | FY08-0006 | P779273 | 550 | S&R 1 lighting & auditorium seat covers | 1148 | Howard |  |  | Def Maint | Other
2010-01-21 | FY08-0007 | P779286 | 593 | HSC Cooling coil replacement | 22351.35 | Sameer |  |  | Energy | HVAC | X
2010-01-22 | FY08-0008 | P779352 | 509 | MD Anderson library envelope seal | 164190.24 | Oliver |  |  | Def Maint | Arch | X
2010-01-22 | FY08-0009 | P779353 | 701 | TMC Pharmacy roof assessment | 88517.69 | Oliver |  |  | Def Maint | Arch
2010-01-25 | FY08-0010 | P779354 | 543 | Architecture guttering assessment | 124749.48 | Oliver |  |  | Def Maint | Arch
2010-01-26 | FY08-0011 | P779355 | 106 | TLCC Anex roof collapse repair | 34059 | Gill |  |  | Def Maint | Arch | X
2010-01-25 | FY08-0012 | P779356 | 516 | Framework model addition | 24440 | LaMontagne |  |  | Def Maint | Other | X
2010-01-26 | FY08-0013 | P779289 |  | Diesel tank farm landscaping | 4019.25 | Jenkins |  |  | Def Maint | L&M
2010-01-29 | FY08-0014 | P779359 | 537 | Law Ctr water filtration assessment | 75000 | Doyle |  |  | Def Maint | Safety | X
2010-01-29 | FY08-0015 | P779360 | 543 | Architecture brick ledge repairs | 201105.15 | Oliver |  |  | Def Maint | Arch
2010-01-29 | FY08-0016 | P779361 | 516 | E. Cullen drain scope for blockage | 73098.34 | Jenkins |  |  | Def Maint | Arch | X
2010-02-03 | FY08-0017 | P779362 | 509 | MD Anderson guttering assessment | 39351.84 | Oliver |  |  | Def Maint | Arch | X
2010-02-04 | FY08-0018 | P779363 | 578 | Agnes Arnold cooling coils replacement | 8405 | Madrigal |  |  | Energy | HVAC | X
2010-02-04 | FY08-0019 | P779364 | 551 | S&R2 C/W coil replacement | 7125 | Madrigal |  |  | Energy | HVAC | X
2010-02-05 | FY08-0020 | P779365 | 593 | HSC coils, dampers & air grilles | 18000 | Sameer |  |  | Energy | HVAC
2010-04-05 | FY08-0021 | P779366 | 590 | Hilton storm pump controllers | 3800 | Bartow |  |  | Def Maint | Elec
2010-02-05 | FY08-0022 | P779367 | 499 | Campus fire alarm network | 3009 | Sameer |  |  | Def Maint | Safety | X
2010-02-11 | FY08-0023 | P779368 | 524 | Student Svs. Replace elevator flooring | 1895 | Oliver | 1895 | Closed | Def Maint | Safety | X
2010-02-11 | FY08-0024 | P779369 | 586 | Cameron sanitary line replacement | 40461 | Gill |  |  | Def Maint | Plumbing | X
2010-02-12 | FY08-0025 | P779370 | 544 | Cemo tunnel 6" water line leak repair | 1801.38 | Gill |  |  | Def Maint | Plumbing | X
2010-02-22 | FY08-0026 | P779372 | 585-516-532-543 | Asbestos sample testing for 4 buildings | 513.31 | Wright | 513.31 | Closed | Def Maint | L&M
2010-02-22 | FY08-0027 | P779373 | 536 | CPB replace broken window | 632 | Wright | 632 | Closed | Def Maint | Arch | X
2010-02-15 | FY08-0028 | P779374 | 581 | Engineering fire alarm upgrade | 304116 | Jenkins |  |  | Def Maint | Safety
2010-02-15 | FY08-0029 | P779375 | 585 | GSB fire alarm upgrade | 321148 | Jenkins |  |  | Def Maint | Safety
2010-02-23 | FY08-0030 | P779376 | 590 | Hilton sump pump monitor alarms | 5737 | Maal |  |  | Def Maint | Other | X
2010-02-22 | FY08-0031 | P779377 | 520 | School of Music storm drain assessment | 5017 | Gill |  |  | Def Maint | Plumbing | X
2010-03-02 | FY08-0032 | P779378 | 550 | S&R 1 rm 325 ACM abatement | 4133 | Doyle |  |  | Def Maint | L&M | X
2010-03-03 | FY08-0033 | P779380 | 586 | Cameron Human/Hlth kitchen trap repair | 9177.3 | Oliver |  |  | Def Maint | Plumbing | X
2010-03-03 | FY08-0034 | P779381 | 535 | EHRM 2 drainage repair | 43100.29 | Jenkins | 43100.29 | Closed | Def Maint | Plumbing | X
2010-03-03 | FY08-0035 | P779382 | N/A | Campus wide card access license | 4120 | Jenkins |  |  | Def Maint | Safety | X
2010-03-04 | FY08-0036 | P779384 | 532 | Garrison carpet replacement | 4742.28 | Villarreal |  |  | Def Maint | Arch
2010-03-04 | FY08-0037 | P779385 | 585 | GSB rm 177 carpet replacement | 5032.34 | Villarreal |  |  | Def Maint | Arch
2010-03-04 | FY08-0038 | P779386 | N/A | Campus wide sprinkler deficiencies | 21313.32 | Sameer |  |  | Def Maint | L&M | X
2010-04-07 | FY08-0039 | P779411 | 550 | S&R 1 emergency water leaks | 108000 | Oliver |  |  | Def Maint | Plumbing | X
2010-04-07 | FY08-0040 | P779412 | 544 | Cemo Hall water infiltration in tunnel | 53820 | Miller |  |  | Def Maint | Arch | X
2010-04-13 | FY08-0041 | P779413 | 564 | Fleming hot water pipe leaks | 2308 | Wright |  |  | Def Maint | Plumbing | X
2010-04-19 | FY08-0042 | P779414 | 585 | GSB paint booth system replacement | 66000 | Oliver |  |  | Def Maint | Arch
2010-04-20 | FY08-0043 | P779415 | 505 | Optometry animal care plumbing leak study | 4221 | Javaid |  |  | Def Maint | Plumbing | X
2010-04-22 | FY08-0044 | P779416 | 499/ 516 | E Cullen emergency water line repairs | 20737.5 | Oliver |  |  | Def Maint | Plumbing | X
2010-04-22 | FY08-0045 | P779417 | 589 | Fine Arts organ recital hall ceiling repair | 56804 | Doyle |  |  | Def Maint | Arch
2010-04-23 | FY08-0046 | P779418 | 586 | Cameron sewage line investigation | 1915 | Oliver | 1915 | Closed | Def Maint | Plumbing | X
2010-04-23 | FY08-0047 | P779419 | 520 | Moore School of Music structural Review | 28915.36 | Lawrence |  |  | Def Maint | Arch | X
2010-04-22 | FY08-0048 | P779420 | 590 | Hilton (cont. ed) parking garage appraisal | 6669.21 | Lawrence | 6669.21 | Closed | Def Maint | Arch
2010-04-27 | FY08-0049 | P779421 | N/A | Campus wide condition assessment update | 325369 | Norcom |  |  | Def Maint | Other
2010-04-29 | FY08-0050 | P779423 | 578 | Agnes Arnold chill water coil replacement | 3500 | Madrigal |  |  | Energy | HVAC | X
2010-04-29 | FY08-0051 | P779424 | 501 | Roy Cullen repair transfer switch controller | 19825 | Bartow |  |  | Energy | HVAC
2010-05-03 | FY08-0052 | P779425 | 509 | MDA Library emergency water main break | 4707.1 | Wright |  |  | Def Maint | Plumbing | X
2010-04-29 | FY08-0053 | P779426 |  | Engineering complex transfer switch repair | 14860 | Bartow |  |  | Energy | HVAC | X
2010-04-30 | FY08-0054 | P779427 | 551 | S&R 2 replace drainage plumbing in 439 | 5000 | Javaid |  |  | Def Maint | Plumbing
2010-05-04 | FY08-0055 | P779428 | 509 | MDA Library hand dryer project | 53721.8 | Jenkins |  |  | Def Maint | Arch | X
2010-05-04 | FY08-0056 | P779429 | 579 | Engineering asbestos abatement 2nd floor | 5184 | Madrigal |  |  | Def Maint | L&M | X
2010-05-05 | FY08-0057 | P779430 | 579 | Engineering asbestos abatement 3rd floor | 5184 | Madrigal |  |  | Def Maint | L&M | X
2010-05-05 | FY08-0058 | P779431 | 550 | S&R 1 protective structures for loading dock and entrance | 64250 | Doyle |  |  | Def Maint | Safety | X
2010-05-17 | FY08-0059 | P779435 | 529 | SEC emergency lighting configuration | 3703 | Doyle |  |  | Def Maint | Arch | X
2010-05-21 | FY08-0060 | P779437 | 528 | Melcher water leak in crawlspace | 8000 | Madrigal |  |  | Def Maint | Plumbing | X
2010-09-13 | FY08-0061 | P779487 | 590 | Continuing Education ADA Uprades | 3678.13 | Jenkins |  |  | Def Maint | L&M |  | deferred
2010-09-13 | FY08-0062 | P779488 | 529 | SER Classroom JCI HVAC Controllers | 21867.76 | Martin |  |  | Energy | HVAC |  | Planned
2010-09-21 | FY08-0063 | P779490 | 499 | Valve replacement near Lot 19E | 8315 | Gill |  |  | Def Maint | Plumbing | X | Critical
2010-09-27 | FY08-0064 | P779492 | 550 | S&R1 sewer ejector system | 18468 | Wright |  |  | Def Maint | Plumbing | X | Critical
2010-09-29 | FY08-0065 | P779493 | 512 | Mobile office park restroom awning (classroom facility) | 2583.24 | Davis |  |  | Def Maint | Arch |  | Deferred
2010-09-29 | FY08-0066 | P779494 | 528 | MelcherHall handrail repair | 1210.25 | Jenkins |  |  | Def Maint | Arch | X | Critical
2010-10-11 | FY08-0067 | P779495 | 509 | MD Anderson bad odor in basement | 7210 | Gill |  |  | Def Maint | HVAC | X | Critical
2010-10-11 | FY08-0068 | P779496 | 543 | Architecture indoor air quality assessment | 21958.5 | Oliver |  |  | Def Maint | HVAC |  | Deferred
2010-10-12 | FY08-0069 | P779497 | 543 | Architecture 4th floor air balance | 12460 | Martin |  |  | Def Maint | HVAC | X | Deferred
2010-10-14 | FY08-0070 | P779498 | 553 | Welcome Center sewer gas odor investigation | 3240 | Wright |  |  | Def Maint | Plumbing |  | Deferred
2010-10-26 | FY08-0071 | P779499 | 516 | E. Cullen TDLR upgrades, signage, access buttons, handicap parking striping, etc | 8352 | Wiesman |  |  |  | L&M
2010-10-28 | FY08-0072 | P779500 | 507 | Wortham Theater mold & mildew cleaning | 881.8 | Norcom |  |  |  | Other | X | Deferred
2010-12-17 | FY08-0073 | P779506 | 551 | S&R2 SDS vent stack smoke testing | 2500 | Gill |  |  |  | Plumbing | X | Critical
2011-02-28 | FY08-0074 | P779521 | 515 | Chiller 2A motor repair | 75000 | Robinson |  |  |  | HVAC | X | Critical
2010-01-04 | FY09-0001 | P779346 | 587 | Farish Hall classroom 232 doors | 4748.75 | Barnes |  |  | Def Maint | Arch | X
2010-01-08 | FY09-0002 | P779349 | 543 | Architecture Enviro investigation | 97785.36 | Oliver | 97785.36 | Closed | Def Maint | L&M
2010-01-15 | FY09-0003 | P779351 | 543 | Architecture leak investigation | 211004.46 | Oliver | 132529.87 | Closed | Def Maint | Arch
2010-03-04 | FY09-0004 | P779383 | 543 | Architecture fire alarm replacement | 280180.4 | Sameer |  |  | Def Maint | L&M
2010-03-09 | FY09-0005 | P779387 | N/A | Campus wide Basic card access controls | 104599.88 | Jenkins |  |  | Def Maint | Safety | X
2010-03-10 | FY09-0006 | P779388 | 551 | S&R 2 trench drain cleaning | 3054.24 | Barnes |  |  | Def Maint | Plumbing
2010-03-12 | FY09-0007 | P779389 | 499 | Lynn Eusan park sanitary line replace | 29701 | Gill |  |  | Def Maint | Plumbing | X
2010-03-22 | FY09-0008 | P779390 | 524 | Student Svs. Bldg new fire alarm system | 116744 | Doyle |  |  | Def Maint | Safety
2010-03-23 | FY09-0009 | P779391 | N/A | Campus wide fire alarm network breakout | 63758.44 | Hajecate |  |  | Def Maint | Safety
2010-03-24 | FY09-0010 | P779392 | N/A | Campus wide infrastructure study | 145950 | Sameer |  |  | Def Maint | Other | X
2010-03-25 | FY09-0011 | P779393 | 549 | Modify lighting for projection in Social Work rm 101 auditorium | 8121.8 | Jenkins |  |  | Def Maint | Arch
2010-03-25 | FY09-0012 | P779394 | 549 | Modify lighting for projection in Social Work rm 102 auditorium | 11339.95 | Jenkins |  |  | Def Maint | Arch | X
2010-03-25 | FY09-0013 | P779396 | 506 | Communications replace airhandling units | 324850 | Ruck |  |  | Def Maint | Arch | X
2010-03-25 | FY09-0014 | P779397 | 530 | Fire hydrant replacement near Robertson stadium | 7485 | Oliver | 7485 | Closed | Def Maint | L&M | X
2010-03-25 | FY09-0015 | P779398 | 516 | E. Cullen restroom modifications for TDLR | 400 | Howard |  |  | Def Maint | L&M
2010-03-31 | FY09-0016 | P779399 |  | Arch & Eng. Study of E. Cullen, PGH, Fleming & Agnes Arnold | 51346 | Norcom |  |  | Def Maint | Arch
2010-03-31 | FY09-0017 | P779400 | 516 | E. Cullen 3rd flr air return obstruction | 7360 | Martin |  |  | Energy | HVAC | X
2010-04-01 | FY09-0018 | P779401 | 516 | E.Cullen 1st flr rm 125, door and fire alarm devices | 2365.27 | Norcom | 2365.27 | Closed | Def Maint | L&M | X
2010-03-31 | FY09-0019 | P779402 | 509 | MD Anderson design MEP systems | 72460.5 | Jenkins |  |  | Def Maint | Arch | X
2010-04-01 | FY09-0020 | P779403 | 528 | Melcher Hall recycling center | 1920.23 | Wright |  |  | Def Maint | Arch
2010-04-01 | FY09-0021 | P779404 | 505 | Optometry termite treatment | 17030.16 | Wright |  |  | Def Maint | Arch | X
2010-03-31 | FY09-0022 | P779405 | 525 | Health Ctr replace controller transfer switch | 1730.4 | Bartow |  |  | Def Maint | Elec | X
2010-03-31 | FY09-0023 | P779406 | 505 | Optometry replace controller transfer switch | 2438.01 | Bartow |  |  | Def Maint | Elec | X
2010-03-31 | FY09-0024 | P779408 | 515 | Locate covered manhole near Justin Dart | 1771.6 | Bartow |  |  | Def Maint | Other | X
2010-04-01 | FY09-0025 | P779409 | 516 | E. Cullen rm 209 & 27 recarpet | 768 | Jenkins |  |  | Def Maint | Arch | X
2010-04-01 | FY09-0026 | P779410 | N/A | Campus wide detention bank map updates | 8500 | LaMontagne |  |  | Def Maint
2010-05-01 | FY09-0027 | P779433 | 501 | R. Cullen HVAC repairs & fire damper install | 3675 | Oliver |  |  | Energy | HVAC | X
2010-05-12 | FY09-0028 | P779434 | 520 | Moores Music handrail install | 20994.05 | Jenkins |  |  | Def Maint | Arch | X
2010-05-21 | FY09-0029 | P779438 | 543 | Architecture AHU drain pan and piping | 3181.22 | Madrigal |  |  | Def Maint | HVAC | X
2010-05-21 | FY09-0030 | P779439 | 551 | SR II lab 329 replace faulty HVAC controls | 7120 | Martin |  |  | Def Maint | HVAC | X
2010-05-27 | FY09-0031 | P779441 | N/A | Utility infrastructure study for entire campus chilled water & steam | 51500 | Sameer |  |  | Energy | Other
2010-06-01 | FY09-0032 | P779442 | 515 | 8" water valve replacement Central Plant | 4785 | Gill |  |  | Def Maint | Plumbing
2010-06-10 | FY09-0033 | P779443 | 516 | E. Cullen 1st floor hallway reflooring | 26673.28 | Davis |  |  | Def Maint | Arch | X
2010-06-23 | FY09-0034 | P779449 |  | Irrigation loop at OB woods | 10924.95 | Smith |  |  | Def Maint | Plumbing | X
2010-08-04 | FY09-0035 | P779474 | 509 | MD Anderson exterior façade | 200000 | Oliver |  |  | Def Maint | Arch | X
2011-03-08 | FY09-0036 | P779523 |  | Fire Extinguisher replacement | 11350 | Tremont |  |  |  | Safety | x | On-going
2011-03-21 | FY09-0037 | P779526 | 564 | Fleming, Domestic Hot Water Repair | 2767 | Wright |  |  |  | Plumbing | X | Critical
| FY09-0038 | P779530 | 579 | Cullen Engineering Limited Asbestos Training | 383 | Wiesman |  |  |  | L&M |  | Deferred
2010-04-26 | FY10-0001 | P779422 | N/A | Campus Design Guideline Standards | 225000 | Yancey |  |  | Other | Arch
2010-05-14 | FY10-0002 | P779436 | 564 | Fleming classrooms #154, 160 & 162 | 423881 | Davis |  |  | Def Maint | Arch | X
2010-08-04 | FY10-0003 | P779474 | 509 | MD Anderson exterior façade | 842638.42 | Oliver |  |  | Def Maint | Arch | X
2010-08-23 | FY11-0001 | P779481 | 515 | FY11 CRDM Central Plant Expansion | 4996670 | Bueller |  |  | Def Maint | Other | X
2010-09-09 | FY11-0002 | P779486 | N/A | Main Campus Utility Documentation | 335280 | Ivy |  |  | Energy | Other |  | Planned
2010-11-03 | FY11-0003 | P779502 | 524 | Student Svs. Bldg replace 2 roof skylights that are leaking in rain | 3509.32 | Jenkins |  |  |  | Arch | X | Critical
2010-11-15 | FY11-0004 | P779503 | 532 /533 | Hallway floor abatement at Melcher & Garrison | 52363.46 | Wiesman |  |  |  | Arch |  | Deferred
2010-11-30 | FY11-0005 | P779504 | N/A | Campus wide Honeywell controller replacement | 14789.73 | Martin |  |  |  | HVAC | X | Deferred
2010-12-22 | FY11-0006 | P779509 | 509 | MD Anderson water damage carpet replacement | 28590.34 | Jenkins |  |  |  | Safety | X | Critical
2011-01-24 | FY11-0007 | P779510 | 509 | MD Anderson Library Exterior Assessment | 54105.9 | Oliver |  |  |  | Arch |  | Planned
2011-02-24 | FY11-0008 | P779513 | 549 | Social Work Fire Pump Replacement | 24837.4 | Hajecate |  |  |  | Safety | x | Planned
2011-02-24 | FY11-0009 | P779515 | N/A | Water, Sanitary, Storm Master Plan | 170000 | Ivy |  |  |  | Other |  | Deferred
2011-02-24 | FY11-0010 | P779516 | N/A | Transportation Master Plan | 140000 | Ivy |  |  |  | Other |  | Deferred
2011-02-24 | FY11-0011 | P779517 | 571 | Y Building Study and Design Phase I and II | 206485.39 | Norcom |  |  |  | Other |  | Facility
2011-02-24 | FY11-0012 | P779518 | N/A | Campus Wide Ruptured Coil Replacement | 356895 | Oliver |  |  |  | HVAC | x | Critical | Changed to Ledger 2 in anticipation of Insurance claim
2011-02-28 | FY11-0013 | P779519 | 550 /551 | Installation of 1500kW, 1875kVA Generator in addition to SR1 & SR2 | 246990.29 | Kapileshwari |  |  |  | Elec | x | Facility
2011-03-04 | FY11-0014 | P779522 | 579 | Cullen Engineering Flooring Replacement | 11899.33 | Davis |  |  |  | L&M | x | Deferred
2011-03-08 | FY11-0015 | P779524 | 579 | Cullen Engineering Fire Suppression Pump Design and Installation | 379065.75 | Kapileshwari |  |  |  | Safety | x | Critical
2011-03-17 | FY11-0016 | P779525 | 505 | Optometry Exterior façade study | 20600 | Norcom |  |  |  | Other |  | Facility
2011-03-21 | FY11-0017 | P779527 | 515 | Chiller 2A Motor Rewind | 158467.63 | Gill |  |  |  | HVAC | X | Critical
2011-03-25 | FY11-0018 | P779528 | 507 | Wortham Theater Room 100M-100D Door Replacement | 28750.7 | Brungardt |  |  |  | Other |  | Deferred
2011-04-06 | FY11-0019 | P779529 | 543 | College of Architecture Mold Remediation | 6407.12 | Oliver |  |  |  | L&M | x | Deferred
2011-04-07 | FY11-0020 | P779531 | N/A | FCA Phase 1 and 2 | 95176.33 | Norcom |  |  |  | Other |  | Facility
2011-04-14 | FY11-0021 | P779532 | 499 | Campus Fire Hydrant #9 | 9717.28 | Oliver |  |  |  | Safety | x | Facility
2011-04-14 | FY11-0022 | P779533 | 501 | Roy Cullen Exterior Façade Study | 56650 | Connell |  |  |  | Arch |  | Deferred
2011-04-15 | FY11-0023 | P779534 | N/A | U of H Generator & ATS Remote Operation | 49965 | Gill |  |  |  | Elec |  | Facility
2011-04-19 | FY11-0024 | P779535 | 545 | SERC Transite Pipe Repair | 6776.64 | Ivy |  |  |  | Plumbing | x | Deferred
2011-04-20 | FY11-0025 | P779536 | 551 | SR2 Animal Care HVAC Commissioning | 112315.32 | Oliver |  |  |  | HVAC | x | Deferred
2011-04-20 | FY11-0026 | P779537 | 555 | Law Residence Hall Sewer Line Replacement | 10235.76 | Gill |  |  |  | Plumbing | x | Deferred
2011-04-20 | FY11-0027 | P779538 | 585/586 | GSB/Cameron Hot Water boilers/HVAC systems | 27604 | Gill |  |  |  | Plumbing | x | Deferred
2011-04-20 | FY11-0028 | P779539 | 516 | E Cullen/Campus wide Floodbreak repair & annual Maintenance inspection | 11540 | Gill |  |  |  | Other | x | Planned
2011-04-20 | FY11-0029 | P779540 | 550 | SR1 Window replacement | 3211 | Wright |  |  |  | Other | x | Critical
2011-04-20 | FY11-0030 | P779541 | 516 | E Cullen Window replacement Rooms 6 & 8 | 1431 | Wright |  |  |  | Other | x | Critical
2011-05-03 | FY11-0031 | P779542 | 516 | E Cullen Install ADA Automatic Door Opener | 4074.5 | Wright |  |  |  | L&M |  | Facility
2011-05-03 | FY11-0032 | P779543 | 590 | Hilton Window Replacement First Floor West | 1873 | Wright |  |  |  | Other | x | Critical
2011-05-03 | FY11-0033 | P779544 | 593 | Houston Science Center Window Replacement | 1928.2 | Wright |  |  |  | Other | x | Critical
2011-05-03 | FY11-0034 | P779545 | 590 | Hilton (E&G) Controls Upgrade | 302511 | Wright |  |  |  | HVAC |  | Facility
2011-05-03 | FY11-0035 | P779546 | 524 | Health Center Room 126 Window Replacement | 654 | Wright |  |  |  | Other | x | Critical
2011-05-03 | FY11-0036 | P779547 | 586 | Cameron Smoke Test Sanitary Lines/Video Inspection/Hydro-jet cleaning | 46448 | Gill |  |  |  | Plumbing | x | Deferred
2011-05-03 | FY11-0037 | P779548 | 550 | Repair breaker at SR1 | 72000 | Rahurkar |  |  |  | Elec | x | Deferred
2011-05-13 | FY11-0038 | P779549 | 581 | Cullen Engineering W409 Carrier Roof Top replacement | 23811.25 | Oliver |  |  |  | HVAC | x | Planned
2011-05-13 | FY11-0039 | P779550 | N/A | Entrance 14 Curb modifications | 19071.79 | Ivy |  |  |  | Other | x | Deferred
2011-05-19 | FY11-0040 | P779551 | 564 | Fleming Domestic Hot Water Pipe Repair | 4148 | Wright |  |  |  | Plumbing | x | Critical
2011-05-19 | FY11-0041 | P779552 | N/A | Exterior Concrete Stair repair | 66346.84 | Connell |  |  |  | Other |  | Deferred
2011-05-19 | FY11-0042 | P779553 | 579 | Cullen Eng. Chill Water Leak Water Mitigation and Recovery | 20682.83 | Wiesman |  |  |  | HVAC | x | Critical
2011-05-19 | FY11-0043 | P779554 | 499 | Campus Wide Fire Extinguisher Replacement | 14986.5 | Oliver |  |  |  | Other | x | Deferred
2011-06-01 | FY11-0044 | P779556 | N/A | UH Campus Room Signs | 18000 | Wanjagi |  |  |  | Other | x | Deferred
2011-06-01 | FY11-0045 | P779557 | 590 | Water Leak outside Continuing Education Building | 15148 | Gill |  |  |  | Plumbing | x | Critical
2011-06-01 | FY11-0046 | P779558 | 516 | E. Cullen Basement Floor Repair | 40640.31 | Jenkins |  |  |  | Other |  | Deferred
2011-06-01 | FY11-0047 | P779559 | 551 | SR2 Animal Care Sanitary Clean Outs Installation | 11093 | Gill |  |  |  | Plumbing | x | Facility
2011-06-01 | FY11-0048 | P779560 | 543 | College of Architecture Visible Mold Remediation | 107789.98 | Oliver |  |  |  | Safety | x | Critical
2011-06-23 | FY11-0049 | P779562 | 523 | AGL Domestic Water Leak | 52957.92 | Gill |  |  |  | Plumbing | x | Critical
2011-06-23 | FY11-0050 | P779563 | 593 | HSC Mold Remediation in Dark Room | 9011.05 | Jenkins |  |  |  | Other | x | Deferred
2011-06-23 | FY11-0051 | P779564 | 585 | GSB 1st Floor Restroom compliance renovation | 13518.75 | Jenkins |  |  |  | L&M |  | Facility
2011-06-30 | FY11-0052 | P779565 | 586 | Cameron cleanup of abandoned grease trap | 5847.84 | Gill |  |  |  | Other | x | Deferred
2011-07-12 | FY11-0053 | P779566 | 515 | Central Plant Chiller #4 York 4000 Tom Emergency Service | 124452.31 | Gill |  |  |  | HVAC | x | Deferred
2011-07-13 | FY11-0054 | P779567 | 499 | Main Leak by Moody/Hilton area | 161695 | Gill |  |  |  | Plumbing | x | Critical
2011-07-13 | FY11-0055 | P779568 | 512 | Trailer Village Utility Disconnects and Decking Adjustments | 5665 | Ivy |  |  |  | Elec |  | Facility
2011-07-13 | FY11-0056 | P779569 | 516 | E. Cullen Domestic Booster Pumps | 13143 | Gill |  |  |  | Plumbing | x | Deferred
2011-07-18 | FY11-0057 | P779570 | 581 | Domestic Water leak on northside of Engineering | 2603.94 | Gill |  |  |  | Plumbing | x | Critical
2011-07-28 | FY11-0058 | P779571 | 507 | Wortham Theater Awning Removal | 1030 | Ivy |  |  |  | Other | x | Deferred
2011-07-06 | FY11-0059 | P779572 | 578 | Agnes Arnold Hall Classroom 104, 106, 108, and 110 Refresh | 176505.94 | Connell |  |  |  | Other | x | Deferred
2011-08-12 | FY11-0060 | P779575 | 528 | Melcher Hall Exterior Handrails | 53154.36 | Jenkins |  |  |  | Safety | x | Critical
2011-08-26 | FY11-0061 | P779577 | 586 | Cameron Vent Piping for Water heaters & emergency generator | 26944 | Gill |  |  |  | HVAC | x | Critical
2011-08-30 | FY11-0062 | P779578 | 555 | Law Residence Hall water main leak | 20630 | Gill |  |  |  | Plumbing | x | Critical
2011-09-06 | FY11-0063 | P779579 | 509 | MDA Library 8" Ductile iron water main break | 2664 | Gill |  |  |  | Plumbing | x | Critical
2011-09-06 | FY11-0064 | P779580 | 499 | Parking Lot 19-D 8" water main break | 3326 | Gill |  |  |  | Plumbing | x | Critical
2011-09-06 | FY11-0065 | P779581 | 539 | Krost Hall 6" water main break | 3138.63 | Gill |  |  |  | Plumbing | x | Critical
2011-09-06 | FY11-0066 | P779582 | 527 | Science and Engineering Classroom Shade Protection Rails | 53652.09 | Connell |  |  |  | Other |  | Deferred
2011-09-06 | FY11-0067 | P779583 | 579 | Cullen Engineering ADA/TAS Compliancy | 30790.03 | Oliver |  |  |  | L&M | x | Deferred
2011-09-07 | FY11-0068 | P779584 | 499 | 8" water main break in front of SR1 | 8461 | Gill |  |  |  | Plumbing | x | Critical
2011-09-12 | FY11-0069 | P779585 | 551 | SR2 resolve ongoing Termite problems, Dr. F. Lamar Pritchards Office Rm. #141D | 5799.07 | Tolbert |  |  |  | Other | x | Deferred
2011-09-12 | FY11-0070 | P779586 | 543 | College of Architecture Phase 3 of Indoor Air Quality Issues | 45633 | Oliver |  |  |  | HVAC |  | On-Going
2011-09-12 | FY11-0071 | P779587 | 543 | College of Architecture Emergency Response Sprinkler Head Leak | 6577.52 | Oliver |  |  |  | Plumbing | x | Critical
2011-09-16 | FY11-0072 | P779588 | 579 | Cullen Engineering Mechanical Room Containment Phase 1 | 25970 | Oliver |  |  |  | Other | x | Critical
2011-09-16 | FY11-0073 | P779589 | 549 | Graduate School of Social Work Water Damaged Carpet Removal & Replacement | 9516.15 | Jenkins |  |  |  | Other |  | Deferred
2011-09-14 | FY11-0074 | P779590 | 508 | College of Technology ADA Automatic Doors | 3975 | Jenkins |  |  |  | L&M
2011-09-19 | FY11-0075 | P779591 | 542 | South Park Annex East Awning Replacement | 46932.49 | Ivy |  |  |  | Other |  | Facility
2011-09-20 | FY11-0076 | P779592 | 551 | SR2-Animal Care - Hydro Jet clean gravity sanitary drain in Basement | 7220 | Gill |  |  |  | Plumbing | x | On-Going
2011-09-20 | FY11-0077 | P779593 | 499 | 4" irrigation pipe replacement east side of Heyne | 5120.59 | Gill |  |  |  | Plumbing | x | Critical
2011-09-20 | FY11-0078 | P779594 | 494 | Agnes Arnold Auditorium - water main break | 15308.85 | Gill |  |  |  | Plumbing | x | Critical
2011-09-20 | FY11-0079 | P779595 | 499 | 6" Water main break at Entrance of Law Center | 3676.65 | Gill |  |  |  | Plumbing | x | Critical
2011-09-23 | FY11-0080 | P779596 | 499 | Water leak by parking lot 19-E | 3406.25 | Gill |  |  |  | Plumbing | x | Critical
2011-09-23 | FY11-0081 | P779597 | 594 | Water leak in front of engineering building | 3885.86 | Gill |  |  |  | Plumbing | x | Critical
2011-09-23 | FY11-0082 | P779598 | 588 | New domestic and fire water lines for McElhinney bldg. | 11968 | Gill |  |  |  | Plumbing | x | Deferred
2011-09-27 | FY11-0083 | P779599 | 551 | SR2 AHU#4-D replace hot, Chilled water coils | 6790.3 | Rahurkar |  |  |  | HVAC | x | Deferred
2011-09-29 | FY11-0084 | P779600 | 543 | College of Architecture Room 206 Water Damage | 27421.85 | Simmons |  |  |  | Other | x | Critical
2011-10-03 | FY11-0085 | P779601 | 545 | SERC 1st floor, North Side window replacement | 3190 | Wright |  |  |  | Other | x | Critical
2011-10-03 | FY11-0086 | P779602 | 536 | KUHT window replacement, front entrance | 1894 | Wright |  |  |  | Other | x | Critical
2011-10-03 | FY11-0087 | P779603 | 542 | South Park Exterior Lighting replacement | 11996.32 | Wright |  |  |  | L&M | x | Critical
2011-10-03 | FY11-0088 | P779604 | 588 | McElhineey replace damaged classroom tables | 2980 | Wright |  |  |  | Other | x | Critical
2011-10-03 | FY11-0089 | P779605 | 549 | Grad. School of Social Work, replace water damage carpet | 1511.13 | Jenkins |  |  |  | Other |  | Deferred
2011-10-06 | FY11-0090 | P779606 | 589 | Water leak on NE side of Fine Arts | 12342.2 | Gill |  |  |  | Plumbing | x | Critical
2011-10-06 | FY11-0091 | P779607 | 534 | Water leak on north side of Heyne | 2858 | Gill |  |  |  | Plumbing | x | Critical
2011-10-06 | FY11-0092 | P779608 | 554 | Water leak east side of Biology Greenhouse | 4663 | Gill |  |  |  | Plumbing | x | Critical
2011-10-06 | FY11-0093 | P779609 | 534 | Water leak on South side of Heyne | 3702 | Gill |  |  |  | Plumbing | x | Critical
2011-10-11 | FY11-0094 | P779610 | 503 | Water main break south side of Tech 1 | 11455.2 | Gill |  |  |  | Plumbing | x | Critical
2011-10-11 | FY11-0095 | P779611 | 503 | Water main break east side of Tech 1 | 11398 | Gill |  |  |  | Plumbing | x | Critical
2011-10-11 | FY11-0096 | P779612 | 547 | Water leak by three valve cluster north side of PGH | 14665.53 | Gill |  |  |  | Plumbing | x | Critical
2011-10-11 | FY11-0097 | P779613 | 547 | Water leak on south side of PGH | 4061.52 | Gill |  |  |  | Plumbing | x | Critical
2011-10-11 | FY11-0098 | P779614 | 555 | Water leak on south side of Law hall | 6161.52 | Gill |  |  |  | Plumbing | x | Critical
2011-10-11 | FY11-0099 | P779615 | 509 | Water leak on north side of MDA library | 5639.23 | Gill |  |  |  | Plumbing | x | Critical
2011-10-17 | FY11-0100 | P779617 | 518 | Campus Water infrastructure leak on east side of Calhoun Lofts | 1250.27 | Gill |  |  |  | Plumbing | x | Critical
FY11-0101
2010-08-23 | FY12-0001 | P779482 | 515 | FY12 CRDM Central Plant Expansion | 5903107 | Bueller |  |  | Def Maint | Other | X
22704162.35
2010-08-23 | FY13-0001 | P779483 | 515 | FY13 CRDM Central Plant Expansion | 7325297 | Bueller |  |  | Def Maint | Other | X | Future Planned Expenditures
2010-08-23 | FY14-0001 | P779484 | 515 | FY14 CRDM Central Plant Expansion | 5378122 | Bueller |  |  | Def Maint | Other | X | Future Planned Expenditures