## PFA
UNIVERSITY OF HOUSTON SYSTEM
UNIVERSITY OF HOUSTON
Facilities Planning and Construction
PROJECT NAME
PROJECT FUNDING AGEEMENT (PFA)
|  | Work Order Number: | XXXXXX
|  | Date: | XX/XX/XXXX
This agreement serves to document the initial funding commitments and outline the general assumptions for the project prior to making it active (or the completion of the Memorandum of Understanding).
OVERVIEW
Project Description
PROJECT BUDGET (For bond funding attach the UH CFO fiscal year funding authorization, bond schedule and cash flow assumptions to this agreement)
FUNDING | SOURCE | REVENUE STREAM for BONDS | FUNDS APPROVED TO DATE | PFA | TOTAL
Drop Down (Verify) | Drop Down (Verify) | Drop Down (Verify) |  |  | 0
0
0
0
| Total Anticipated Project Budget | 0 | 0 | 0 | 0
FUNDING COST CENTERS
COST CENTERS |  |  |  | PERCENTAGE | (OR) AMOUNT
|  |  |  | 0% | 0
|  |  |  | 0% | 0
|  |  |  | 0% | 0
|  |  |  | 0% | 0
Total Anticipated Project Budget |  |  |  | 0% | 0
Pursuant to the Board of Regent's Policy No. 53.04, projects equal to or greater than $10,000,000 must obtain Board approval. Any budget increases exceeding an aggregate amount of $1,000,000 must obtain additional Board approval.
Does not require Board approval |  | Requires Board approval |  | Requires additional Board approval
FUNDING REQUIREMENTS and INFORMATION
● In order for the project to proceed into procurement of services this funding must be transferred to Facilities Planning and Construction. A cost center will be created exclusively for this project and a reconciliation will be performed monthly and made available for your review.
● Prior to advertising for construction, full project funding is required and must be transferred to the project or bond arrangements for funding based on fiscal year must be authorized by the UH CFO in writing with supporting bond schedule and cash flow assumptions and attached to this agreement.
● The Total Project Budget may decrease and/or increase throughout the bidding, design, construction and close out phases of the project. Modifications are typically due to scope revisions and unforeseen conditions. If this occurs an addendum to this Project Funding Agreement will be prepared and distributed to the stakeholders below for approval.
● If the project does not proceed to the construction phase the funding cost center(s) will be responsible for all costs incurred prior to cancellation, including system project management fees.
● Attachments: | 1. Project Information and Data Sheet
2. Project Control Budget
APPROVAL
| Nicholas Tamayo | Planning, Facilities Planning & Construction |  | DATE:
| Jeanne LaMontagne | Planning, Facilities Planning & Construction |  | DATE:
| Katherine Miller | Planning, Facilities Planning & Construction |  | DATE:
| XXXXXXXXXX | Customer |  | DATE:
| XXXXXXXXXX | Customer |  | DATE:
UNIVERSITY OF HOUSTON SYSTEM
UNIVERSITY OF HOUSTON
PROJECT NAME
PROJECT INFORMATION AND DATA SHEET
|  | Work Order Number: | XXXXXX
|  | Date: | XX/XX/XXXX
University of Houston Campus: |  | Drop Down (Verify) | FP&C Planner:
College / Entity: |  | Drop Down (Verify) | FP&C PPM:
Client Contact Name: |  |  | FP&C PM Name:
Client Phone: |  |  | FP&C PM Phone:
Client Email: |  |  | FP&C PM Email:
PROJECT DESCRIPTION
Project Description
PROJECT SCOPE OF WORK
PROJECT ASSUMPTIONS
1.
2.
3.
4.
5.
PROJECT CONSTRAINTS / RISKS:
1.
2.
3.
4.
5.
CUSTOMER REQUESTED MILESTONE SCHEDULE:
SCOPE DEVELOPMENT | XX/XX/XXXX | NOTES:
DESIGN | XX/XX/XXXX | NOTES:
CONSTRUCTION | XX/XX/XXXX | NOTES:
COMPLETION DATE | XX/XX/XXXX | NOTES:

## PCB
UNIVERSITY OF HOUSTON SYSTEM
UNIVERSITY OF HOUSTON
Facilities Planning and Construction
PROJECT NAME
PROJECT CONTROL BUDGET (PCB)
|  |  | Project Number: |  | TBD
|  |  | Project Budget: |  | 200000
|  |  | Date: |  | XX/XX/XXXX
COST CATEGORY |  |  | ORIGINAL BUDGET | % CCL | %TPC | NOTES
A. Construction Costs
| ASBESTOS REMOVAL (Omit?) |  | 0 | 0% | 0%
| DEMOLITION (Omit?) |  | 0 | 0% | 0%
| LANDSCAPING (SITE WORK) (Omit?) |  | 0 | 0% | 0%
| CONSTRUCTION CONTRACT |  | 100000 | 100% | 50%
|  | CCL (Construction) Subtotal | 100000 | 100% | 50%
| IT/SECURITY EQUIPMENT |  | 0 | 0% | 0%
| A/V EQUIPMENT |  | 0 | 0% | 0%
| FURNITURE AND MOVABLE EQUIPMENT |  | 0 | 0% | 0%
|  | Construction and FFE Total | 100000 | 100% | 50%
B. Professional Services
| A/E PROGRAMMING FEES (Omit?) |  | 0 | 0% | 0%
| A/E BASIC FEES |  | 0 | 0% | 0%
| A/E REIMBURSABLES |  | 0 | 0% | 0%
| PRECONSTRUCTION SERVICES (Move Up?) |  | 0 | 0% | 0%
| SYSTEM PROJECT MGMT (Verify % of TPC) |  | 0 | 0% | 0% | NOTE: Add drop down. 6% = 5.67 5% = 4.76
| GEOTECHNICAL ENGINEERING |  | 0 | 0% | 0%
| ENVIRONMENTAL SURVEY |  | 0 | 0% | 0%
| SITE SURVEY |  | 0 | 0% | 0%
| MATERIALS TESTING |  | 0 | 0% | 0%
| AUDIT FEES |  | 0 | 0% | 0%
| COMMISSIONING |  | 0 | 0% | 0%
| TESTING BALANCING |  | 0 | 0% | 0%
| BUILDING ENVELOPE QA/QC CONSULTANT |  | 0 | 0% | 0%
| WATER / WASTE WATER FEES |  | 0 | 0% | 0%
| ASBESTOS CONSULTING |  | 0 | 0% | 0%
| OTHER |  | 0 | 0% | 0%
|  | Professional Services Total | 0 | 0% | 0%
C. Administrative Costs
| ART |  | 0 | 0% | 0%
| CONSTRUCTION WEBCAM |  | 0 | 0% | 0%
| SHOP SUPPORT |  | 0 | 0% | 0%
| MOVING/MISC |  | 0 | 0% | 0%
| PROJECT CONTINGENCY (% OF TPC) |  | 100000 | 100% | 50%
|  | Administrative Total | 100000 | 100% | 50%
TOTAL PROJECT COST (TPC) |  |  | 200000
| CONTRACTOR CONTINGENCY |  | 0 |  |  | (Within Construction Contract)
APPROVAL (Is this still being signed or only the PFA?)
| Planning PM, Facilities Planning & Construction |  |  | DATE: | Executive Director, Facilities Planning & Construction DATE:
| Planning Manager, Facilities Planning & Construction |  |  | DATE: | Customer | DATE:
Note on D36: If adding line items, set up links

## PTB
UNIVERSITY OF HOUSTON SYSTEM
UNIVERSITY OF HOUSTON
Facilities Planning and Construction
PROJECT NAME
PROJECT TRACKING BUDGET (PTB)
200000
|  |  | A | B | C | D | E | F
COST CATEGORY |  |  | ORIGINAL BUDGET | CURRENT COMMITMENTS | COMMITMENTS INVOICED | BALANCE OF COMMITMENTS D = B - C | PROJECTED COST-TO-COMPLETE | PROJECTED (OVER)/UNDER F = A - E | NOTES
A. Construction Costs
| ASBESTOS REMOVAL |  | 0 | 0 | 0 | 0 | 0 | 0
| DEMOLITION |  | 0 | 0 | 0 | 0 | 0 | 0
| LANDSCAPING (SITE WORK) |  | 0 | 0 | 0 | 0 | 0 | 0
| CONSTRUCTION CONTRACT |  | 100000 | 0 | 0 | 0 | 113000 | -13000
|  | CCL (Construction) Subtotal | 100000 | 0 | 0 | 0 | 113000 | -13000
| IT/SECURITY EQUIPMENT |  | 0 | 0 | 0 | 0 | 0 | 0
| A/V EQUIPMENT |  | 0 | 0 | 0 | 0 | 0 | 0
| FURNITURE AND MOVABLE EQUIPMENT |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction and FFE Total | 100000 | 0 | 0 | 0 | 113000 | -13000
B. Professional Services
| A/E PROGRAMMING FEES |  | 0 | 0 | 0 | 0 | 0 | 0
| A/E BASIC FEES |  | 0 | 0 | 0 | 0 | 0 | 0
| A/E REIMBURSABLES |  | 0 | 0 | 0 | 0 | 0 | 0
| PRECONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 0 | 0
| SYSTEM PROJECT MGMT (Verify % of TPC) |  | 0 | 0 | 0 | 0 | 0 | 0
| GEOTECHNICAL ENGINEERING |  | 0 | 0 | 0 | 0 | 0 | 0
| ENVIRONMENTAL SURVEY |  | 0 | 0 | 0 | 0 | 0 | 0
| SITE SURVEY |  | 0 | 0 | 0 | 0 | 0 | 0
| MATERIALS TESTING |  | 0 | 0 | 0 | 0 | 0 | 0
| AUDIT FEES |  | 0 | 0 | 0 | 0 | 0 | 0
| COMMISSIONING |  | 0 | 0 | 0 | 0 | 0 | 0
| TESTING BALANCING |  | 0 | 0 | 0 | 0 | 0 | 0
| BUILDING ENVELOPE QA/QC CONSULTANT |  | 0 | 0 | 0 | 0 | 0 | 0
| WATER / WASTE WATER FEES |  | 0 | 0 | 0 | 0 | 0 | 0
| ASBESTOS CONSULTING |  | 0 | 0 | 0 | 0 | 0 | 0
| OTHER |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Professional Services Total | 0 | 0 | 0 | 0 | 0 | 0
C. Administrative Costs
| ART |  | 0 | 0 | 0 | 0 | 0 | 0
| CONSTRUCTION WEBCAM |  | 0 | 0 | 0 | 0 | 0 | 0
| SHOP SUPPORT |  | 0 | 0 | 0 | 0 | 0 | 0
| MOVING/MISC |  | 0 | 0 | 0 | 0 | 0 | 0
| PROJECT CONTINGENCY (% OF TPC) |  | 100000 | 13000 |  |  | 73000 | 27000
|  |  |  | -13000 |  |  | -13000 | 13000 | Formulas: Offset dbl. entries above
|  | Administrative Total | 100000 | 0 | 0 | 0 | 60000 | 40000
TOTAL PROJECT COST (TPC) |  |  | 200000 | 0 | 0 | 0 | 173000 | 27000
| CONTRACTOR CONTINGENCY |  | 0 | 0 | 0 | 0 | 0 | 0 | (Within Construction Contract)
Note on D35: If adding line items, set up links

## AsbestosRem
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Asbestos Removal Fees
Vendor:
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Demolition
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Demolition Fees
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Landspacing
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Landscaping Fees
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## ConstContract
PROJECT: |  | PROJECT NAME
Cost Worksheet For: |  | Construction Contract or CMAR
Vendor:
XYZ Construction
Contract/CO Number |  | Service | Value
W?????? |  | GMP | 0
0
0
|  |  | 0 | Less Payments | Balance
| CONTRACT TOTAL |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
0
0
|  |  | Subtotal | 0
CONTRACTOR CONTINGENCY TRACKING:
# | Item |  |  | Amount:
| Contingency amount: |  |  | 0
Commitments:
1 | Item
2 | Item
3 | Item
4 | Item
5 | Item
6 | Item
7 | Item
8 | Item
9 | Item
10 | Item
11 | Item
12 | Item
13 | Item
14 | Item
15 | Item
16 | Item
17 | Item
18 | Item
Total Commitments:

## IT, Security
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | IT, Security Equipment
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## AV Equipment
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | A/V Equipment
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Furn,MoveEquip
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Furniture and Moveable Equipment
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## AE Program
PROJECT: |  | PROJECT NAME
Cost Worksheet For: |  | A&E PROGRAMMING
Vendor:
Vendor Name
Contract/CO Number |  | Service | Value
| W?????? | Programming
|  |  |  | Less Payments | Balance
Programming Total |  |  | 0 | 0 | 0
Payments
Programming Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
|  |  | Subtotal | 0

## AE Basic
PROJECT: |  | PROJECT NAME
Cost Worksheet For: |  | A&E BASIC
Vendor:
Vendor Name
Contract/CO Number |  | Service | Value
| W?????? | Basic Services
|  |  |  | Less Payments | Balance
Basic Services Total |  |  | 0 | 0 | 0
Payments
Basic Services Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
|  |  | Subtotal | 0

## AE Reimb
PROJECT: |  | PROJECT NAME
Cost Worksheet For: |  | A&E REIMBURSIBLES
Vendor:
Vendor Name
Contract/CO Number |  | Service | Value
| W?????? | REIMBURSIBLES
|  |  |  | Less Payments | Balance
REIMBURSIBLES Total |  |  | 0 | 0 | 0
Payments
REIMBURSIBLES Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
|  |  | Subtotal | 0

## PreconSvc
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Preconstruction Services
Vendor:
UH FP&C
Contract Number |  | Service | Value
N/A |  | Precon Fee | 0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Date Approved | Amount
|  |  | Subtotal | 0

## SysProjMgmt
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | System Project Management
Vendor:
UH FP&C
Contract Number |  | Service | Value
N/A |  | PM Fee | 0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Date Approved | Amount
|  |  | Subtotal | 0

## Geotech
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Geotechnical Engineering
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Enviro
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Environmental Survey
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## SiteSurvey
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Site Survey
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## MatlTest
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Materials Testing
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Audit
PROJECT NAME |  | PROJECT NAME
Cost Worksheet for: |  | Audit Fees
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Commiss
PROJECT NAME |  | PROJECT NAME
Cost Worksheet for: |  | Commissioning
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## TestBal
PROJECT NAME |  | PROJECT NAME
Cost Worksheet for: |  | Testing Balancing
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Bldg Env
PROJECT NAME |  | PROJECT NAME
Cost Worksheet for: |  | Building Envelope and QA/QC Consultant
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## WaterWaste
PROJECT NAME |  | PROJECT NAME
Cost Worksheet for: |  | Water/Waste Water Fees
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Asbestos
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Asbestos Consulting
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Other
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Other (Consultants)
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## Art
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Art
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## ConstWebcam
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Construction Webcam
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## ShopSpt
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Shop Support
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## MovingMisc
PROJECT: |  | PROJECT NAME
Cost Worksheet for: |  | Moving / Misc
Vendor:
Consultant Name
Contract/CO Number |  | Service | Value
0
0
0
0
|  |  |  | Less Payments | Balance
Contract Total |  |  | 0 | 0 | 0
Payments
Contract Payments
| Invoice # | Invoice Date | Approved Date | Amount
0
0
0
|  |  | Subtotal | 0

## ProjConting
OWNER'S CONTINGENCY REPORT
PROJECT: | PROJECT NAME
UPDATED:
OWNER'S CONTINGENCY AMOUNT: | [5 empty] | 100000 | (linked from PTB)
APPROVED ITEMS:
PR # | Ref | ITEM | AMOUNT | STATUS | SUBTOTALS | TOTALS | NOTES:
NA | DCA 1 | Items A, B, C | 1000
NA | DCA 2 | Items A, B, C | 4000
3 | CO 1 | Items A, B, C | 2000 |  |  |  |  | Approved
NA | DCA 3 | Items A, B, C | 3000 |  |  |  |  | Consultant Review
5 | CO 2 | Items A, B, C | 3000 |  |  |  |  | FP&C review
Contractor Pricing
Dispute
|  |  | SUBTOTAL APPROVED CONTINGENCY USE: |  | 13000
PENDING AND POTENTIAL ITEMS:
PR # | Ref | ITEM | AMOUNT
1 |  | Items A, B, C | 1000
2 |  | Items A, B, C | 4000
4 |  | Items A, B, C | 2000
NA | DCA 4 | Items A, B, C | 3000
|  |  | SUBTOTAL PENDING AND POTENTIAL CHANGES: |  | 10000
ESTIMATED FOR UNKNOWNS: |  |  |  |  | 50000
PROJECTED TOTAL CONTINGENCY TO BE USED: |  |  |  |  | 73000
PROJECTED TOTAL CONTINGENCY BALANCE AT END: |  |  |  | TOTAL: |  | 27000
VOID ITEMS:
PR # | Ref | ITEM | AMOUNT
1 |  | Items A, B, C | 1000
2 |  | Items A, B, C | 4000
4 |  | Items A, B, C | 2000
NA | DCA 4 | Items A, B, C | 3000