SECTION 01 2600 - CONTRACT MODIFICATION PROCEDURES

Revise this Section by deleting and inserting text to meet Project-specific requirements.

This Section uses the term "Architect." Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

Delete hidden text after this Section has been edited for the Project.

GENERAL

RELATED DOCUMENTS

Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 01 Specification Sections, apply to this Section.

The Contractor's attention is specifically directed, but not limited, to the following documents for additional requirements:

The current version of the Uniform General Conditions for Construction Contracts, State of Texas, available on the web site of the Texas Facilities Commission.

The University of Houston’s Supplemental General Conditions and Special Conditions for Construction.

SUMMARY

Section includes administrative and procedural requirements for handling and processing Contract modifications. Construction Manager shall develop and implement a system acceptable to Owner for the preparation, review and processing of Change Proposals, contingency and allowance expenditure authorizations, Change Orders, and requests for information, in accordance with the UGC and SGC.

MINOR CHANGES IN THE WORK

Architect will issue supplemental instructions authorizing minor changes in the Work, not involving adjustment to the Contract Sum or the Contract Time, on AIA Document G710, "Architect's Supplemental Instructions" or similar form.

PROPOSAL REQUESTS

Owner-Initiated Proposal Requests:  Architect will issue a detailed description of proposed changes in the Work that may require adjustment to the Contract Sum or the Contract Time.  If necessary, the description will include supplemental or revised Drawings and Specifications.

Always retain first subparagraph below.  Only a Change Order or a Construction Change Directive authorizes Contractor to proceed with a proposed change.

Work Change Proposal Requests issued by Architect are not instructions either to stop work in progress or to execute the proposed change.

Revise 20-day time period in subparagraph below to suit Project; suggested 20-day time period may be too long for many projects.

Within time specified in Proposal Request or 14 days, when not otherwise specified, after receipt of Proposal Request, submit a quotation estimating cost adjustments to the Contract Sum and the Contract Time necessary to execute the change.

Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made.  If requested, furnish survey data to substantiate quantities.

Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.

Include costs of labor and supervision directly attributable to the change.

Include an updated Contractor's construction schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship.  Use available total float before requesting an extension of the Contract Time.

Quotation Form:  Use forms provided by Owner.  Sample copies are included in the Owner’s Supplementary General Conditions for Construction.

Contractor-Initiated Proposals:  If latent or changed conditions require modifications to the Contract, Contractor may initiate a claim by submitting a request for a change to Architect.

Include a statement outlining reasons for the change and the effect of the change on the Work.  Provide a complete description of the proposed change.  Indicate the effect of the proposed change on the Contract Sum and the Contract Time.

Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made.  If requested, furnish survey data to substantiate quantities.

Indicate applicable delivery charges, equipment rental, and amounts of trade discounts.

Include costs of labor and supervision directly attributable to the change.

Include an updated Contractor's construction schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship.  Use available total float before requesting an extension of the Contract Time.

Comply with requirements in Section 01 2500 "Substitution Procedures" if the proposed change requires substitution of one product or system for product or system specified.

Proposal Request Form:  Use form provided by Owner.  Sample copy is included in the Owner’s Supplementary General Conditions for Construction.

ADMINISTRATIVE CHANGE ORDERS

Allowance Adjustment:  See Section 01 2100 "Allowances" for administrative procedures for preparation of Change Order Proposal for adjusting the Contract Sum to reflect actual costs of allowances.

Unit-Price Adjustment:  See Section 01 2200 "Unit Prices" for administrative procedures for preparation of Change Order Proposal for adjusting the Contract Sum to reflect measured scope of unit-price work.

CHANGE ORDER PROCEDURES

On Owner's approval of a Work Change Proposal Request, Architect will issue a Contract Change Order for signatures of Owner and Contractor on Owner’s standard form.

CONSTRUCTION CHANGE DIRECTIVE

Revise below if Owner requires use of a special form.

[Construction] [Work] Change Directive: [Architect] [Construction Manager] may issue a [Construction] [Work] Change Directive on [form included in Project Manual].  [Construction] [Work] Change Directive instructs Contractor to proceed with a change in the Work, for subsequent inclusion in a Change Order.

Construction Change Directive contains a complete description of change in the Work.  It also designates method to be followed to determine change in the Contract Sum or the Contract Time.

Documentation:  Maintain detailed records on a time and material basis of work required by the Construction Change Directive.

After completion of change, submit an itemized account and supporting data necessary to substantiate cost and time adjustments to the Contract.

PRODUCTS (Not Used)

EXECUTION (Not Used)

END OF SECTION 01 2600