University of Houston Master Construction Specifications

<%Insert Project Name%>


Copyright 2010 by The American Institute of Architects (AIA)

Exclusively published and distributed by Architectural Computer Services, Inc. (ARCOM) for the AIA

SECTION 011000 - SUMMARY
Revise this Section by deleting and inserting text to meet Project-specific requirements.

PART 1 -  GENERAL

1.1 RELATED DOCUMENTS

Retain or delete this article in all Sections of Project Manual.

A. Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 01 Specification Sections, apply to this Section.

1.2 SUMMARY

A. Section Includes:

1. Project information.

2. Work covered by Contract Documents.

3. Phased construction.

4. Work by Owner.

5. Work under separate contracts.

6. Future work.

7. Purchase contracts
8. Salvage requirements.

9. Owner-furnished products.

10. Contractor-furnished, Owner-installed products.

11. Access to site.

12. Coordination with occupants.

13. Work restrictions.

14. Specification and drawing conventions.

15. Miscellaneous provisions.

B. Related Requirements:

Retain subparagraph below to cross-reference requirements Contractor might expect to find in this Section but are specified in other Sections.

1. Section 015000 "Temporary Facilities and Controls" for limitations and procedures governing temporary use of Owner's facilities.

1.3 PROJECT INFORMATION

A. Project Identification:  <Insert Project identifier such as Project name and number>.

1. Project Location:  <Insert Project location (street address, city, and state)>.

B. Owner:  <Insert name and address of Owner>.

1. Owner's Representative:  <Insert name and contact information for Owner's representative>.

C. Architect:  <Insert name and contact information for Architect>.

Retain "Architect's Consultants" Paragraph below if providing contact information for Architect's consultants for Project use.

D. Architect's Consultants:  The Architect has retained the following design professionals who have prepared designated portions of the Contract Documents:

Copy and re-edit subparagraph below for each consultant.  Coordinate with requirement in Section 012900 "Payment Procedures" to arrange schedule of values data by design consultant contracts for purposes of delineating the scopes of multiple certifications of payments.

1. <Insert title of design discipline>:  <Insert name and contact information for consultant>.

Retain "Other Owner Consultants" Paragraph below if Owner has retained design consultants, in addition to Architect, under separate contract(s).

E. Other Owner Consultants:  The Owner has retained the following design professionals who have prepared designated portions of the Contract Documents:

Copy and re-edit subparagraph below for each consultant.  Coordinate with requirement in Section 012900 "Payment Procedures" to arrange schedule of values data by design consultant contracts for purposes of delineating the scopes of multiple certifications of payments.

1. <Insert title of design discipline>:  <Insert name and contact information for consultant>.  <Insert title of design discipline> has prepared the following portions of the Contract Documents:

a. <Insert description of scope of service for other Owner consultant>.

Retain "Contractor" Paragraph below only if Contractor is selected by negotiation and if subcontracts are subsequently bid.

F. Contractor:  <Insert name and contact information for Contractor> has been engaged as Contractor for this Project.

Retain "Construction Manager" Paragraph below if Owner has engaged a construction manager.

G. Construction Manager:  <Insert name and contact information for Construction Manager>.

Retain one of two subparagraphs below.  Retain first subparagraph for Construction Manager in the role of advisor when Owner directly contracts with subcontractors; retain second subparagraph for Construction Manager in the role of constructor who in turn subcontracts portions of the Work.

1. Construction Manager has been engaged for this Project to serve as an advisor to Owner and to provide assistance in administering the Contract for Construction between Owner and[ each] Contractor, according to a separate contract between Owner and Construction Manager.

2. Construction Manager for this Project is Project's constructor.  The terms "Construction Manager" and "Contractor" are synonymous.

Retain "Design-Builder" Paragraph below for design-build projects.

H. Design-Builder:  <Insert name and contact information for Design-Builder>.

Revise subparagraph below to accurately describe contract structure of Project.

1. Design-Builder has been engaged for this Project to provide architectural and engineering services and to serve as Project's constructor.  The terms "Design-Builder" and "Contractor" are synonymous.

Retain "Project Web Site" Paragraph below if Project uses a project Web site, project extranet, or FTP site for information and document management.

I. Project Web Site:  A project Web site administered by [Architect] [Owner] [Construction Manager] [Contractor] will be used for purposes of managing communication and documents during the construction stage.

Retain subparagraph below and coordinate specific Contractor requirements related to Project Web site with Section 013100 "Project Management and Coordination."

1. See Section 013100 "Project Management and Coordination." for requirements for [establishing] [administering] [and] using the Project Web site.

1.4 WORK COVERED BY CONTRACT DOCUMENTS

In first paragraph below, include an abbreviated description of the Work for Project identified in "Project Information" Article.  See Evaluations.  For single prime contracts, this article may be eliminated.

A. The Work of Project is defined by the Contract Documents and consists of the following:

1. <Insert a brief description of Project indicating the size, code classification for occupancy and construction type, and general description of major building assemblies>.

Insert additional paragraphs for other major items of work.  See Evaluations for model text.

B. Type of Contract:

Retain one of two subparagraphs below.

1. Project will be constructed under a single prime contract.

2. Project will be constructed under coordinated, concurrent multiple contracts.  
Copy and re-edit subparagraph below to identify names of multiple contracts.  See Evaluations for model text.

a. <Insert name of the Contract>.

1.5 PHASED CONSTRUCTION

Retain this article if phased construction with multiple Certificates of Substantial Completion is required.  See Evaluations.

Revise first paragraph below to suit Project.  See Evaluations for model text.

A. The Work shall be conducted in <Insert number> phases, with each phase substantially complete as indicated:

Copy and re-edit first subparagraph below for each phase required.  See Evaluations for model text.

1. Phase <Insert designation>:  <Briefly describe work of this phase> Work of this phase shall commence [within <Insert number of days> after the Notice to Proceed] [by <Insert date>] and be substantially complete and ready for occupancy [within <Insert number of days>] [after the Notice to Proceed] [after commencement of construction of this phase] [by <Insert date>].

2. Phase <Insert designation>:  The remaining Work shall be substantially complete and ready for occupancy at time of Substantial Completion for the Work.

B. Before commencing Work of each phase, submit an updated copy of Contractor's construction schedule showing the sequence, commencement and completion dates[, and move-out and -in dates of Owner's personnel] for all phases of the Work.

1.6 WORK BY OWNER

Retain this article if work under this Contract depends on successful completion of work performed by Owner.  See Evaluations.

A. General:  Cooperate fully with Owner so work may be carried out smoothly, without interfering with or delaying work under this Contract or work by Owner.  Coordinate the Work of this Contract with work performed by Owner.

Retain "Preceding Work" Paragraph below if work by Owner is expected to be complete before work under this Contract begins.  Revise to suit Project.  See Evaluations for model text.

B. Preceding Work:  Owner will perform the following construction operations at Project site.  Those operations are scheduled to be substantially complete before work under this Contract begins.

Copy and re-edit subparagraph below for each separate category of work to be performed by Owner.

1. <Insert a brief description of work performed by Owner>.

Retain "Concurrent Work" Paragraph below if work by Owner will be conducted concurrently with work under this Contract.  Revise to suit Project.  See Evaluations for model text.

C. Concurrent Work:  Owner will perform the following construction operations at Project site.  Those operations will be conducted simultaneously with work under this Contract.

Copy and re-edit subparagraph below for each separate category of work to be performed by Owner.

1. <Insert a brief description of work performed by Owner>.

Retain "Subsequent Work" Paragraph below if future work to be performed by Owner depends on successful completion of work performed under this Contract.  Revise to suit Project.  See Evaluations for model text.

D. Subsequent Work:  Owner will perform the following additional work at site after Substantial Completion.  Completion of that work will depend on successful completion of preparatory work under this Contract.

Copy and re-edit subparagraph below for each separate contract.

1. <Insert a brief description of work performed by Owner>.

1.7 WORK UNDER SEPARATE CONTRACTS

Retain this article if work under this Contract depends on successful completion of work performed under separate contracts.  See Evaluations.

A. General:  Cooperate fully with separate contractors so work on those contracts may be carried out smoothly, without interfering with or delaying work under this Contract or other contracts.  Coordinate the Work of this Contract with work performed under separate contracts.

Retain "Preceding Work" Paragraph below if work under separate contracts is expected to be complete before work under this Contract begins.  Revise to suit Project.  See Evaluations for model text.

B. Preceding Work:  Owner [has awarded] [will award] separate contract(s) for the following construction operations at Project site.  Those operations are scheduled to be substantially complete before work under this Contract begins.

Copy and re-edit subparagraph below for each separate contract.

1. <Insert name of the Contract>:  To <Insert name of separate Contractor> [to] [for] <Insert a brief description of work performed under separate contract>.

Retain "Concurrent Work" Paragraph below if work under separate contracts is conducted concurrently with work under this Contract.  Revise to suit Project.  See Evaluations for model text.  Where significant concurrent work occurs that requires definition of scopes and the services of a Project coordinator, delete below and use Section 011200 "Multiple Contract Summary" for description of work of separate contracts.

C. Concurrent Work:  Owner [has awarded] [will award] [and will assign to Contractor] separate contract(s) for the following construction operations at Project site.  Those operations will be conducted simultaneously with work under this Contract.

Copy and re-edit subparagraph below for each separate contract.

1. <Insert name of the Contract>:  To <Insert name of separate Contractor> [to] [for] <Insert a brief description of work performed under separate contract>.

Retain "Subsequent Work" Paragraph below if work under future contracts depends on successful completion of work performed under this Contract.  Revise to suit Project.  See Evaluations for model text.

D. Subsequent Work:  Owner [has awarded] [will award] separate contract(s) for the following additional work to be performed at site following Substantial Completion.  Completion of that work will depend on successful completion of preparatory work under this Contract.

Copy and re-edit subparagraph below for each separate contract.

1. <Insert name of the Contract>:  To <Insert name of separate Contractor> [to] [for] <Insert a brief description of work performed under separate contract>.

1.8 FUTURE WORK

Retain this article when allowance has been made in the design for future work such as additions or equipment installation or change-out that requires special consideration during executing of the Work.  Revise to suit Project.

A. The Contract Documents include requirements that will allow Owner to carry out future work following completion of this Project; provide for the following future work:

1. <Insert description of future work requiring consideration during construction of the Work of this Contract>.

1.9 PURCHASE CONTRACTS

This article is an example of a requirement best described in this Section.  Retain if Owner orders or negotiates products or equipment in advance.  See Evaluations.

A. General:  Owner has negotiated purchase contracts with suppliers of material and equipment to be incorporated into the Work.  Owner will assign these purchase contracts to Contractor.  Include costs for purchasing, receiving, handling, storage if required, and installation of material and equipment in the Contract Sum, unless otherwise indicated.

1. Contractor's responsibilities are same as if Contractor had negotiated purchase contracts, including responsibility to renegotiate purchase and to execute final purchasing agreements.

Copy and re-edit "Purchase Contracts Information" Paragraph below for each purchase contract to accurately represent extent of Contractor's responsibility for each item.

B. Purchase Contracts Information:

1. <Insert product name>:  See Section <Insert Section number> "<Insert Section title>."

a. Purchase Contract Firm and Representative:  <Insert name and contact information for purchase contract firm and representative.>

b. Purchase Contract Scope:  [Furnishing material] [Material and installation labor] <Insert description of contract>.

c. Purchase Status:  [Price negotiated by Owner, to be incorporated in the Contract Sum by Contractor; see Section 012100 "Allowances" for cash allowance for purchase contract] [Price negotiated and incorporated in the Contract Sum by Contractor] [Product reserved by Owner] [Order placed and deposit paid by Owner] [Order to be placed by Contractor] <Insert description of status of purchase contract>.

d. Quantity:  <Insert quantity ordered>.

e. Other Requirements:  <Insert special requirements>.

1.10 SALVAGE REQUIREMENT

Salvage requirements are also addressed in SECTION 02 41 19 - SELECTIVE STRUCTURE DEMOLITION, SECTION 31 11 00 - CLEARING AND GRUBBING, SECTION 01 31 00 - PROJECT MANAGEMENT AND COORDINATION, SECTION 28 05 00 -- COMMON WORK RESULTS FOR ELECTRONIC SAFETY AND SECURITY, SECTION 28 05 00 -- COMMON WORK RESULTS FOR COMMUNICATIONS, SECTION 04 20 00 - UNIT MASONRY, SECTION 23 03 00 - BASIC MATERIALS AND METHODS, SECTION 23 01 00 – MECHANICAL GENERAL PROVISIONS.  Ensure that sections included among the project specifications agree with these provisions.
A. Unless otherwise indicated, demolition waste becomes property of Contractor. 
B. Unless otherwise indicated, all equipment that must be removed due to interference with work of this contract remains the property of the Owner, and may be salvaged at the Owner's discretion.
C. On LEED-certified projects, additional requirements may apply.  Consult other sections for specific LEED procedures.

D. Owner wishes to salvage, refurbish, and/or reuse the following materials and store and/or reinstall as itemized below.  Drawings also may indicate items to be salvaged and stored on Owner's premises and the location of storage.  Coordinate all salvage activities with FP&C Project Manager. [Note that salvage disposition may also be treated as a construction alternate: in these situations include salvage information on GMP Exhibit A-2, APPROVED AND ACCEPTED ALTERNATES.]
Item No. ___: ________________________________________________________________________

Handling [Contractor shall remove and relocate to Owner’s designated location] [Contractor shall remove and stockpile on the project site] [Contractor shall refurbish and reinstall as indicated in the Project documents] [Contractor shall reinstall as indicated in the Project documents]: ________________________________________________________________
Salvage Value (assigned by [Contractor] [Owner]): ________________________________________
Repeat as necessary.
E. Materials and/or items scheduled above for relocation and which are damaged during dismantling or reassembly operations shall be repaired and restored to good operative condition.  The Contractor may, at his discretion and upon the approval of the Owner, substitute new materials and/or items of like design and quality in lieu of materials and/or items to be relocated  

1.11 OWNER-FURNISHED PRODUCTS

This article defines responsibilities of Owner and Contractor for Owner-furnished products.

Retain first paragraph below if Owner furnishes products for a project.  Revise to suit Project.  See Evaluations for model text.

A. Owner will furnish products indicated.  The Work includes receiving, unloading, handling, storing, protecting, and installing Owner-furnished products[ and making building services connections].

B. Owner-Furnished Products:

1. <Insert description, in separate subparagraphs, for each Owner-furnished product>.

1.12 CONTRACTOR-FURNISHED, OWNER-INSTALLED PRODUCTS

This article defines responsibilities of Owner and Contractor for Contractor-furnished, Owner-installed items.

Retain first paragraph below if Contractor furnishes products for a project that will subsequently be installed by Owner.  Revise to suit Project.  See Evaluations for model text.

A. Contractor shall furnish products indicated.  The Work includes unloading, handling, storing, and protecting Contractor-furnished products as directed and turning them over to Owner at Project closeout.

B. Contractor-Furnished, Owner-Installed Products:

1. <Insert description, in separate subparagraphs, for each Contractor-furnished, Owner-installed product>.

1.13 ACCESS TO SITE

Retain one of two "General" paragraphs below.  Retain first paragraph if Project is on a vacant site or in an unoccupied building being renovated and there are no Owner-occupancy requirements.  Retain second if Owner will occupy portions of an existing site or building.  Revise to suit Project.

A. General:  Contractor shall have full use of Project site for construction operations during construction period.  Contractor's use of Project site is limited only by Owner's right to perform work or to retain other contractors on portions of Project.

B. General:  Contractor shall have limited use of Project site for construction operations as indicated on Drawings by the Contract limits and as indicated by requirements of this Section.

Retain "Use of Site" Paragraph below if Project site is accessible to other parties or if parts of a building being renovated are occupied during construction.  Revise to suit Project.  See Evaluations for model text.

C. Use of Site:  Limit use of Project site to [work in areas] [areas within the Contract limits] indicated.  Do not disturb portions of Project site beyond areas in which the Work is indicated.

Retain first "Limits" Subparagraph below on projects where necessary to describe areas of a site where work is permitted.  Expand to indicate areas of site where incursions are forbidden under any circumstances.  See Evaluations for model text.

1. Limits:  Confine construction operations to <Insert description of areas where work is permitted>.

Retain "Limits" Subparagraph below for greenfield sites if reduced site disturbance is required for LEED-NC, LEED-CS, or LEED for Schools Credit SS 5.1.  See Evaluations.

2. Limits:  Limit site disturbance, including earthwork and clearing of vegetation, to 40 feet (12.2 m) beyond building perimeter; 10 feet (3 m) beyond surface walkways, patios, surface parking, and utilities less than 12 inches (300 mm) in diameter; 15 feet (4.5 m) beyond primary roadway curbs and main utility branch trenches; and 25 feet (7.6 m) beyond constructed areas with permeable surfaces (such as pervious paving areas, stormwater detention facilities, and playing fields) that require additional staging areas in order to limit compaction in the constructed area.

"Driveways, Walkways and Entrances" Subparagraph below is an example of a special requirement appropriate to many projects.  Revise to suit Project or delete.

3. Driveways, Walkways and Entrances:  Keep driveways[ parking garage,] [ loading areas,] and entrances serving premises clear and available to Owner, Owner's employees, and emergency vehicles at all times.  Do not use these areas for parking or storage of materials.

a. Schedule deliveries to minimize use of driveways and entrances by construction operations.

b. Schedule deliveries to minimize space and time requirements for storage of materials and equipment on-site.

Insert other paragraphs, as appropriate, describing additional limitations on use of site by construction personnel.  See Evaluations for model text.

Retain "Condition of Existing Building" Paragraph below if the Work involves existing occupied building.

D. Condition of Existing Building:  Maintain portions of existing building affected by construction operations in a weathertight condition throughout construction period.  Repair damage caused by construction operations.

Insert additional paragraphs specifying specific limitations on use of existing building.  See Evaluations for model text.

1.14 COORDINATION WITH OCCUPANTS

Retain "Full Owner Occupancy" Paragraph below if Owner will occupy all or part of premises during construction.  Revise to suit Project.  See Evaluations.

A. Full Owner Occupancy:  Owner will occupy site and [existing] [adjacent] building(s) during entire construction period.  Cooperate with Owner during construction operations to minimize conflicts and facilitate Owner usage.  Perform the Work so as not to interfere with Owner's day-to-day operations.  Maintain existing exits unless otherwise indicated.

1. Maintain access to existing walkways, corridors, and other adjacent occupied or used facilities.  Do not close or obstruct walkways, corridors, or other occupied or used facilities without written permission from Owner and approval of authorities having jurisdiction.

2. Notify Owner not less than [72] <Insert number> hours in advance of activities that will affect Owner's operations.

B. Partial Owner Occupancy:  Owner will occupy the premises during entire construction period, with the exception of areas under construction.  Cooperate with Owner during construction operations to minimize conflicts and facilitate Owner usage.  Perform the Work so as not to interfere with Owner's operations.  Maintain existing exits unless otherwise indicated.

1. Maintain access to existing walkways, corridors, and other adjacent occupied or used facilities.  Do not close or obstruct walkways, corridors, or other occupied or used facilities without written permission from Owner and authorities having jurisdiction.

2. Provide not less than [72] <Insert number> hours' notice to Owner of activities that will affect Owner's operations.

Retain "Owner Limited Occupancy of Completed Areas of Construction" Paragraph below if Owner might occupy completed portions of building before Substantial Completion.  Revise to suit Project.

C. Owner Limited Occupancy of Completed Areas of Construction:  Owner reserves the right to occupy and to place and install equipment in completed portions of the Work, prior to Substantial Completion of the Work, provided such occupancy does not interfere with completion of the Work.  Such placement of equipment and limited occupancy shall not constitute acceptance of the total Work.

Retain subparagraphs below that describe procedures and requirements that may be necessary before limited Owner occupancy of portions of Project.  Revise to suit Project.

1. Architect will prepare a Certificate of Substantial Completion for each specific portion of the Work to be occupied prior to Owner acceptance of the completed Work.

2. Obtain a Certificate of Occupancy from authorities having jurisdiction before limited Owner occupancy.

3. Before limited Owner occupancy, mechanical and electrical systems shall be fully operational, and required tests and inspections shall be successfully completed.  On occupancy, Owner will operate and maintain mechanical and electrical systems serving occupied portions of Work.

4. On occupancy, Owner will assume responsibility for maintenance and custodial service for occupied portions of Work.

1.15 WORK RESTRICTIONS

A. Work Restrictions, General:  Comply with restrictions on construction operations.

1. Comply with limitations on use of public streets and with other requirements of authorities having jurisdiction.

B. On-Site Work Hours:  Limit work in the existing building to normal business working hours of <Insert time> a.m. to <Insert time> p.m., Monday through Friday, unless otherwise indicated.

1. Weekend Hours:  <Insert restrictions on times permitted for weekend work>.

2. Early Morning Hours:  <Insert restrictions or references to regulations by authorities having jurisdiction for restrictions on noisy work>.

3. Hours for Utility Shutdowns:  <Insert Owner's restrictions>.

4. Hours for [Core Drilling] <Insert noisy activity>:  <Insert Owner's restrictions>.

Retain "Existing Utility Interruptions" Paragraph below for existing utilities.  Coordinate with requirements for temporary utilities specified in Section 015000 "Temporary Facilities and Controls."

C. Existing Utility Interruptions:  Do not interrupt utilities serving facilities occupied by Owner or others unless permitted under the following conditions and then only after providing temporary utility services according to requirements indicated:

1. Notify [Architect] [Construction Manager] [Owner] not less than [two] <Insert number> days in advance of proposed utility interruptions.

2. Obtain [Architect's] [Construction Manager's] [Owner's] written permission before proceeding with utility interruptions.

Retain "Noise, Vibration, and Odors" Paragraph below for work in or near occupied facilities.

D. Noise, Vibration, and Odors:  Coordinate operations that may result in high levels of noise and vibration, odors, or other disruption to Owner occupancy with Owner.

1. Notify [Architect] [Construction Manager] [Owner] not less than [two] <Insert number> days in advance of proposed disruptive operations.

2. Obtain [Architect's] [Construction Manager's] [Owner's] written permission before proceeding with disruptive operations.

E. Nonsmoking Building:  As of March 1, 2013, the University of Houston is a non-smoking campus. Smoking is not permitted within the building or on the construction site.
Retain remaining paragraphs to correspond to Owner's requirements.  Revise to suit Project.  Where Owner's requirements are extensive, refer to and insert Owner policy and procedure documents to the Project Manual.

F. Controlled Substances:  Use of tobacco products and other controlled substances [within the existing building] [on Project site] is not permitted.

G. Employee Identification: Owner will provide identification tags for Contractor personnel working on Project site.  Require personnel to use identification tags at all times.

H. Employee Screening:  Comply with Owner's requirements for [drug] [and] [background] screening of Contractor personnel working on Project site.

1. Maintain list of approved screened personnel with Owner's representative.

Insert additional paragraphs to specify restrictions on Contractor's use of premises or to specify limitations because of Owner occupancy.

1.16 SPECIFICATION AND DRAWING CONVENTIONS

Retain this article or portions of it if an explanation of conventions used in the Specifications and Drawings is necessary.  Revise to suit Project.  See Evaluations.

A. Specification Content:  The Specifications use certain conventions for the style of language and the intended meaning of certain terms, words, and phrases when used in particular situations.  These conventions are as follows:

1. Imperative mood and streamlined language are generally used in the Specifications.  The words "shall," "shall be," or "shall comply with," depending on the context, are implied where a colon (:) is used within a sentence or phrase.

2. Specification requirements are to be performed by Contractor unless specifically stated otherwise.

B. Division 01 General Requirements:  Requirements of Sections in Division 01 apply to the Work of all Sections in the Specifications.

Retain "Drawing Coordination" Paragraph below to explain relationship between Drawing information and Specification content.  Revise to suit Project.

C. Drawing Coordination:  Requirements for materials and products identified on Drawings are described in detail in the Specifications.  One or more of the following are used on Drawings to identify materials and products:

1. Terminology:  Materials and products are identified by the typical generic terms used in the individual Specifications Sections.

2. Abbreviations:  Materials and products are identified by abbreviations [published as part of the U.S. National CAD Standard] [and] [scheduled on Drawings].

3. Keynoting:  Materials and products are identified by reference keynotes referencing Specification Section numbers found in this Project Manual.

PART 2 -  PRODUCTS (Not Used)

PART 3 -  EXECUTION (Not Used)

END OF SECTION 011000

AE Project #: <%Project Number%> 
Summary
011000 - 1
Revision Date: 1/29/2018

